## Overview
Trout Threshold ECDSA - MVP Deliverables Tracker (Java)
Project | From-scratch Java implementation of Trout (ACM CCS 2025 / ePrint 2025/1666)
Course | Cybersecurity coursework
Team size | 6 - all developing in Java
Scope of this tracker | MVP / Phase 1 (security-with-abort, target config 2-of-3)
Stack | Java 17+, Maven/Gradle multi-module, JUnit 5, Bouncy Castle (secp256k1), SHA-256
How to use | Owners update Status + % Complete. Filter by Owner for individual task lists.
Status values | Not Started / In Progress / Blocked / In Review / Done
Phase legend | P1 = MVP (must-have, green). P2 = Stretch (bonus, orange).
Critical path | core -> classgroup -> crypto/zk -> protocol -> app. Class group blocks all; start day one.
Java note | Use hand-written trout-wire codec for crypto bytes; never java.io.Serializable. BigInteger is variable-time, so constant-time is out of MVP scope.
Owners (Maven module)
Person A | trout-core - foundations & parameters
Person B | trout-classgroup - class-group arithmetic (critical path)
Person C | trout-crypto - CL encryption & commitments
Person D | trout-zk - zero-knowledge proofs + eVRF
Person E | trout-protocol - DKG, signing, abort
Person F | trout-app + trout-wire - orchestration, tests, demo

## Deliverables
ID | Module | Phase | Deliverable | Description / Acceptance criteria | Owner | Depends on | Est. days | Status | % Complete | Milestone
D01 | trout-wire | P1 | Serialization codec spec | Canonical big-endian byte layout for class-group elements + all messages; round-trips. NOT java.io.Serializable | B/D/F | D11 | 3 | Not Started | 0% | M3
D02 | trout-wire | P1 | Fiat-Shamir transcript spec | Exact absorb order, domain tags, SHA-256 challenge reduction; identical prover/verifier bytes | B/D/F | - | 2 | Not Started | 0% | M3
D03 | trout-core | P1 | Cross-module KAT file | Seeded (deterministic SecureRandom) test vectors all modules assert against | A | - | 2 | Not Started | 0% | M1
D10 | trout-core | P1 | Maven multi-module skeleton | 6 modules wired with dependency edges; CI builds; JUnit runs | A/F | - | 2 | Not Started | 0% | M1
D11 | trout-core | P1 | BigInteger fixed-width helpers | toFixed/fromFixed big-endian padding; round-trip tests | A | D10 | 2 | Not Started | 0% | M1
D12 | trout-core | P1 | Prime & discriminant generation | genPrime + genDiscriminant meeting paper size/form conditions | A | D11 | 3 | Not Started | 0% | M1
D13 | trout-core | P1 | Public parameter setup | setup(lambda) -> Params, transparent, no trusted secret | A | D12 | 2 | Not Started | 0% | M1
D14 | trout-core | P1 | Param/KAT unit tests (JUnit) | Seeded reproducibility + independent primality check | A | D13,D03 | 1 | Not Started | 0% | M1
D20 | trout-classgroup | P1 | Bqf type + reduction | reduce() to canonical ¦b¦<=a<=c; KAT vectors | B | D13 | 3 | Not Started | 0% | M1
D21 | trout-classgroup | P1 | Composition | compose() Gauss schoolbook; KAT vectors | B | D20 | 4 | Not Started | 0% | M1
D22 | trout-classgroup | P1 | Exponentiation + inverse | exp() square-and-multiply, inverse(); homomorphism property test | B | D21 | 3 | Not Started | 0% | M1
D23 | trout-classgroup | P1 | Canonical serialization | serialize/deserialize per D01; round-trip test | B | D21,D01 | 2 | Not Started | 0% | M3
D24 | trout-classgroup | P2 | Best-effort constant-time exp | Documented experiment; note JVM limits (HLD 6.4) | B | D22 | 6 | Not Started | 0% | M6
D30 | trout-crypto | P1 | CL keygen | clKeygen(params) -> ClKeyPair | C | D22 | 2 | Not Started | 0% | M2
D31 | trout-crypto | P1 | CL encrypt / decrypt | Round-trip clDecrypt(clEncrypt(m))==m incl. dlog-in-F step | C | D30 | 4 | Not Started | 0% | M2
D32 | trout-crypto | P1 | Homomorphic ops | clAdd + clScalar; homomorphism JUnit tests | C | D31 | 2 | Not Started | 0% | M2
D33 | trout-crypto | P1 | Commitment scheme | commit/open, hiding+binding; tamper tests reject | C | D22 | 3 | Not Started | 0% | M2
D40 | trout-zk | P1 | Transcript builder | Transcript(absorb/challenge) per D02 (SHA-256) | D | D02 | 2 | Not Started | 0% | M3
D41 | trout-zk | P1 | Sigma proof: dlog | prove/verify knowledge of discrete log in class group | D | D40,D22 | 3 | Not Started | 0% | M3
D42 | trout-zk | P1 | Sigma proof: encCorrect | Ciphertext encrypts a committed value; completeness+soundness tests | D | D41,D32,D33 | 4 | Not Started | 0% | M3
D43 | trout-zk | P1 | Additional relations (Appendix A) | Remaining MVP relations needed by signing | D | D41 | 4 | Not Started | 0% | M3
D44 | trout-zk | P2 | Exponent-VRF (eVRF) | DDH-based eVRF construction + tests | D | D42 | 7 | Not Started | 0% | M6
D50 | trout-protocol | P1 | Party state machine | sealed ProtocolMessage; INIT/DKG/READY/SIGN/ABORT transitions | E | D32,D33,D43 | 2 | Not Started | 0% | M4
D51 | trout-protocol | P1 | DKG rounds 1-2 | Commit-then-reveal coeffs; share distribution (private channel) | E | D50 | 4 | Not Started | 0% | M4
D52 | trout-protocol | P1 | DKG finalize / VSS verify | All honest parties derive same pubKey; consistent shares | E | D51 | 3 | Not Started | 0% | M4
D53 | trout-protocol | P1 | Signing round 1 | Nonce material + ZK proofs per paper | E | D52,D43 | 4 | Not Started | 0% | M5
D54 | trout-protocol | P1 | Signing round 2 + finalize | Combine/decrypt, assemble (r,s); verifies via Bouncy Castle ECDSA | E | D53 | 5 | Not Started | 0% | M5
D55 | trout-protocol | P1 | Abort handling | Failed check -> clean abort with reason | E | D54 | 2 | Not Started | 0% | M5
D56 | trout-protocol | P2 | Scaled decryption | Multiply-encrypted-by-committed + decrypt sub-protocol | E | D54 | 6 | Not Started | 0% | M6
D57 | trout-protocol | P2 | Identifiable Abort | Attribute fault to a specific party | E | D55,D56 | 5 | Not Started | 0% | M6
D58 | trout-protocol | P2 | General t-of-n | Scale beyond 2-of-3 (e.g. 67-of-100) | E | D54 | 4 | Not Started | 0% | M6
D60 | trout-app | P1 | Envelope + transport | JSON envelope (Jackson), broadcast + point-to-point routing | F | D01 | 3 | Not Started | 0% | M4
D61 | trout-app | P1 | Orchestrator (in-JVM mocks) | Virtual-thread party loops with mocked core; unblocks before protocol ready | F | D10 | 3 | Not Started | 0% | M4
D62 | trout-app | P1 | End-to-end integration test | Full 2-of-3 happy path -> verifying signature (JUnit) | F | D54,D60 | 3 | Not Started | 0% | M5
D63 | trout-app | P1 | Fault-injection tests | Dropped/corrupted msg surfaces abort correctly | F | D55,D62 | 2 | Not Started | 0% | M5
D64 | trout-app | P1 | MVP demo | Scripted live 2-of-3 sign + verify (runnable main) | F | D62 | 2 | Not Started | 0% | M5
D65 | trout-app | P2 | Benchmark harness | Time each phase across configs; charts | F | D58 | 4 | Not Started | 0% | M6
D70 | Docs | P1 | HLD document | Architecture, threat model, phasing (this set) | E/F | - | 2 | In Review | 60% | M1
D71 | Docs | P1 | Per-module LLDs | Each owner writes own module LLD | All | D70 | 4 | In Progress | 30% | M3
D72 | Docs | P1 | Final report | Threat model, design rationale, limitations, results | All | D64 | 4 | Not Started | 0% | M5
D73 | Docs | P1 | README + 'not for production' notice | Build/run (mvn) instructions + disclaimer | F | D64 | 1 | Not Started | 0% | M5
Summary
Total deliverables | 41
MVP (P1) count | 35
Stretch (P2) count | 6
MVP est. days (sum) | 97
Done count | 0

## By Owner
Owner | Maven module | MVP deliverable IDs | MVP est. days | Notes
Person A | trout-core | D03,D10*,D11,D12,D13,D14 | 12 | Critical-path feeder; pair with B early; co-owns build skeleton
Person B | trout-classgroup | D01*,D20,D21,D22,D23 | 14 | Hardest module; on critical path; start day one
Person C | trout-crypto | D30,D31,D32,D33 | 11 | Blocked until classgroup exp works
Person D | trout-zk | D02*,D40,D41,D42,D43 | 15 | Owns transcript spec; eVRF is P2
Person E | trout-protocol | D50,D51,D52,D53,D54,D55,D70 | 22 | Densest spec; fill round msgs from paper first
Person F | trout-app + trout-wire | D60,D61,D62,D63,D64,D73 | 14 | Scaffold mocks to start before protocol; co-owns wire+build
* shared/co-owned deliverable. MVP days are core module estimates; docs/tests counted separately.

## Milestones
Milestone | Target | Gate / definition of done | Key deliverables
M1 | Foundations | core + classgroup correct, KAT vectors pass; Maven build green | D03,D10-D14,D20-D22
M2 | Encryption | CL enc + commitments pass round-trip & homomorphic tests | D30-D33
M3 | ZK + spec freeze | Sigma proofs verify; trout-wire serialization/transcript frozen | D01,D02,D23,D40-D43
M4 | DKG | All honest parties derive same pubKey + consistent shares | D50-D52,D60,D61
M5 | MVP DEMO | 2-of-3 end-to-end signature verifies (Phase 1 complete) | D53-D55,D62-D64,D72,D73
M6 | Stretch | eVRF, scaled decryption, IA, t-of-n, best-effort constant-time | D24,D44,D56-D58,D65