## Overview
Class-Group Arithmetic Optimization - Deliverables Tracker
Project | Practical improvement of Trout (ACM CCS 2025 / ePrint 2025/1666)
Improvement | Optimize class-group composition/squaring: schoolbook baseline vs NUCOMP/NUDUPL, with benchmarks
Why it matters | Composition is the dominant cost underneath the whole protocol
Course | Cybersecurity coursework
Team size | 6 - all developing in Java
Stack | Java 17+, Maven/Gradle multi-module, JUnit 5, JMH (Java Microbenchmark Harness)
How to use | Owners update Status + % Complete. Filter by Owner for individual task lists.
Status values | Not Started / In Progress / Blocked / In Review / Done
Phase legend | P1 = MVP baseline+correctness (green). P2 = the optimization & benchmark (orange = stretch/bonus rows).
Correctness rule | Optimized path must equal the baseline reduced form on all inputs (differential oracle).
Benchmark rule | Use JMH, not System.nanoTime - JVM warmup/JIT make naive timing misleading.
Honesty caveat | Mature class-group libs already use NUCOMP; frame the contribution as a controlled Java before/after measurement, not 'paper didn't optimize'.
Owners (Maven module)
Person A | cg-core - Bqf type, partial-GCD primitive, generators (critical-path feeder)
Person B | cg-baseline - schoolbook Gauss compose/reduce/exp (the oracle)
Person C | cg-opt - NUCOMP + NUDUPL (the optimization)
Person D | cg-opt - optimized & multi-exponentiation
Person E | cg-test - differential oracle, property & edge tests
Person F | cg-bench + cg-report - JMH harness, charts, technical report

## Deliverables
ID | Module | Phase | Deliverable | Description / Acceptance criteria | Owner | Depends on | Est. days | Status | % Complete | Milestone
D01 | cg-core | P1 | Maven multi-module skeleton | 6 modules wired; CI builds; JUnit + JMH run | A/F | - | 2 | Not Started | 0% | M1
D02 | cg-core | P1 | Bqf type + GroupOps interface | record Bqf(a,b,c); shared interface both impls satisfy | A | D01 | 2 | Not Started | 0% | M1
D03 | cg-core | P1 | Discriminant & random-form generators | genDiscriminant, randomForm; seeded for KAT/bench | A | D02 | 2 | Not Started | 0% | M1
D04 | cg-core | P1 | Partial extended-GCD primitive | Early-terminating ext-GCD at bound L=floor(¦D¦^1/4); unit-tested vs full GCD | A | D02 | 3 | Not Started | 0% | M1
D05 | cg-core | P1 | KAT vector file + helpers | Deterministic-seed test vectors; toFixed/fromFixed | A | D03 | 2 | Not Started | 0% | M1
D10 | cg-baseline | P1 | Reduction (canonical) | reduce() to ¦b¦<=a<=c with canonical sign rules; KAT | B | D02 | 3 | Not Started | 0% | M2
D11 | cg-baseline | P1 | Schoolbook Gauss composition | compose() per Cohen 5.4.7; KAT vectors | B | D10 | 4 | Not Started | 0% | M2
D12 | cg-baseline | P1 | Binary exponentiation + inverse | square-and-multiply exp(), inverse(); group-law tests | B | D11 | 2 | Not Started | 0% | M2
D13 | cg-baseline | P1 | Baseline group-law test suite | associativity, identity, inverse, exp homomorphism | B | D12 | 2 | Not Started | 0% | M2
D20 | cg-opt | P2 | NUCOMP composition | Optimized compose using partial-GCD; equals baseline after reduce | C | D04,D11 | 5 | Not Started | 0% | M3
D21 | cg-opt | P2 | NUDUPL squaring | Squaring specialization; equals baseline square | C | D20 | 3 | Not Started | 0% | M3
D22 | cg-opt | P2 | Windowed exponentiation | Fixed-window exp; equals binary exp | D | D12 | 3 | Not Started | 0% | M3
D23 | cg-opt | P2 | wNAF exponentiation | Signed sliding window using inverse(); equals binary exp | D | D22 | 3 | Not Started | 0% | M6
D24 | cg-opt | P2 | Multi-exponentiation (Straus/Pippenger) | Product of powers; equals naive loop | D | D22 | 5 | Not Started | 0% | M6
D30 | cg-test | P1 | Differential oracle framework | Run opt vs baseline on seeded + fuzz inputs; record failing seeds | E | D13 | 3 | Not Started | 0% | M3
D31 | cg-test | P2 | NUCOMP/NUDUPL differential tests | compose/square equality across >=3 discriminant sizes | E | D30,D21 | 2 | Not Started | 0% | M3
D32 | cg-test | P1 | Edge-case suite | identity, ambiguous forms (b=0,a=c,¦b¦=a), tiny/huge exponents | E | D30 | 2 | Not Started | 0% | M3
D33 | cg-test | P2 | Exponentiation differential tests | windowed/wNAF/multiExp vs binary | E | D30,D22 | 2 | Not Started | 0% | M3
D34 | cg-test | P1 | Correctness-evidence write-up | 1-page: inputs covered, counts, seeds | E | D31,D32 | 1 | Not Started | 0% | M5
D40 | cg-bench | P1 | JMH harness skeleton | warmup/measurement config, Blackhole, @Param sizes | F | D13 | 3 | Not Started | 0% | M4
D41 | cg-bench | P2 | Compose/square benchmarks | baseline vs NUCOMP/NUDUPL across D sizes | F | D40,D21 | 2 | Not Started | 0% | M4
D42 | cg-bench | P2 | Exponentiation benchmarks | binary vs windowed/wNAF vs exponent size | F | D40,D22 | 2 | Not Started | 0% | M4
D43 | cg-bench | P1 | Result export + charts | CSV/JSON export; time-vs-size charts; speedup table | F | D41 | 2 | Not Started | 0% | M5
D44 | cg-bench | P2 | Multi-exp benchmark | multiExp vs naive loop | F | D40,D24 | 2 | Not Started | 0% | M6
D50 | Docs | P1 | HLD document | Scope, architecture, success criteria (this set) | E/F | - | 2 | In Review | 60% | M1
D51 | Docs | P1 | Per-module LLDs | Each owner writes own module LLD | All | D50 | 3 | In Progress | 30% | M2
D52 | Docs | P1 | Technical report | Method, results, speedup analysis, threats to validity, honesty caveat | All | D43,D34 | 4 | Not Started | 0% | M5
D53 | Docs | P1 | README + 'not for production' notice | Build/run (mvn) + how to reproduce benchmarks | F | D43 | 1 | Not Started | 0% | M5
Summary
Total deliverables | 28
MVP (P1) count | 18
Optimization/stretch (P2) count | 10
Total est. days | 72
Done count | 0

## By Owner
Owner | Maven module | Deliverable IDs | Est. days | Notes
Person A | cg-core | D01*,D02,D03,D04,D05 | 11 | Critical-path feeder; partial-GCD (D04) blocks NUCOMP; pair with C
Person B | cg-baseline | D10,D11,D12,D13 | 11 | Builds the correctness oracle; clarity over speed
Person C | cg-opt (compose) | D20,D21 | 8 | The core optimization; keep differential oracle green
Person D | cg-opt (exp) | D22,D23,D24 | 11 | Windowed exp is P2 core; wNAF/multi-exp are stretch
Person E | cg-test | D30,D31,D32,D33,D34 | 10 | Correctness backbone; owns canonical-form equality
Person F | cg-bench + cg-report | D40,D41,D42,D43,D53 | 10 | JMH methodology is critical; co-owns build skeleton
* co-owned with F (build). Docs (D50-D52) are shared across the whole team.

## Milestones
Milestone | Target | Gate / definition of done | Key deliverables
M1 | Foundations | cg-core: Bqf, generators, partial-GCD, GroupOps; KAT vectors; build green | D01-D05
M2 | Baseline = oracle | Schoolbook compose/reduce/exp correct; group-law tests pass | D10-D13
M3 | Optimization correct | NUCOMP/NUDUPL pass differential oracle vs baseline across sizes | D20,D21,D30-D32
M4 | Measurement sound | JMH harness produces stable numbers across discriminant sizes | D40-D42
M5 | CORE RESULT | Measured speedup + charts + report draft (contribution complete) | D43,D34,D52,D53
M6 | Stretch | wNAF, multi-exponentiation, parameter sweep, paper comparison | D23,D24,D44